CLOUDSERVE SOLUTIONS

# Stage Four: Sprint Plan

Sequencing, estimates, definitions of done and cut order

Draft prepared from the supplied capstone pack and current implementation. Review and personalize before submission.

Project evidence date: 23 October 2026

Estimates below are planning estimates, not claimed actual hours. Enter actual hours in the supplied effort log as work occurs.

# 1. Capacity and sequencing assumptions

Single engineer, three-week capstone; prioritize the unattended CLI gate before optional infrastructure.

The evaluation harness, retrieval and failure isolation are early dependencies.

The optional hosted LLM and Chroma backend must not be required for offline gate execution.

Human review, final report and video require actual student completion; no fake reviewer data or effort hours will be entered.

# 2. Backlog

| ID | Work item | Estimate | Priority | Depends on | Definition of done |
| --- | --- | --- | --- | --- | --- |
| B-01 | Inspect requirements/data and pin environment | 4 h | P0 | — | Schema, acceptance matrix and setup commands documented. |
| B-02 | Normalize channels and output contract | 3 h | P0 | B-01 | All four channels and malformed records covered by tests. |
| B-03 | Build labelled classifier and calibration | 5 h | P0 | B-02 | Intent/urgency/route/answerability scores and alternatives emitted. |
| B-04 | Ingest docs and implement retrieval | 5 h | P0 | B-02 | Stable passage IDs and text; hit-rate metric produced. |
| B-05 | CLI/harness and metrics | 4 h | P0 | B-02 | Arbitrary input path processes full batch unattended. |
| B-06 | Routing and safety overrides | 4 h | P0 | B-03/B-04 | Deterministic thresholds and mandatory review rules tested. |
| B-07 | Response generation and validation | 5 h | P0 | B-04/B-06 | Evidence template and optional OpenRouter; guardrails can block. |
| B-08 | SQLite audit log | 2 h | P0 | B-05/B-06 | Logged count reconciles with output. |
| B-09 | Validation threshold analysis | 5 h | P0 | B-03–B-07 | Threshold sweep, metrics and limitations documented. |
| B-10 | FastAPI and Prometheus | 3 h | P1 | B-07/B-08 | Health, processing and metrics endpoints smoke-tested. |
| B-11 | CI and fault-injection tests | 4 h | P0 | B-01–B-10 | Single documented test command passes; outage fallback covered. |
| B-12 | Clean-copy rehearsal and packaging | 3 h | P0 | B-11 | README reproduced in fresh directory; ZIP inspected. |
| B-13 | Human review, report and video | Student estimate | P0 | B-09–B-12 | Two-reviewer audit, report and demo recorded honestly. |

# 3. Daily checkpoints

| Checkpoint | Deliverable | Status in current package |
| --- | --- | --- |
| Day 1 | Four-channel ingestion | Implemented and tested. |
| Day 2 | Traceable retrieval | Implemented; lexical TF-IDF default, Chroma optional. |
| Day 3 | Classification/routing/logging | Implemented; calibrated model and policy gates. |
| Day 4 | Generation and guardrails | Implemented; tests cover prompt injection, PII and provider outage. |
| Day 5 | Full unattended validation | 80/80 records processed and logged in local validation run. |
| Week 3 | Monitoring, CI, governance and communication | Core files provided; clean-copy test and human review still required by the student. |

# 4. Cut order

First defer dashboard polish, not Prometheus metrics.

Second defer Chroma embeddings comparison, not the deterministic retriever.

Third defer non-essential API features, not CLI/harness reliability.

Never remove safety gates merely to raise automation rate.